## SAW Matrix
| Simple | Medium | Complex | Very Complex | URL to deliverable
Pre-Project Work
Supplier Evaluation | X | X | X | X
Business Case Support | Minimal | Moderate | Full | Full
Strategy and Roadmap |  |  | X | X
Requirements Impact & Gap Analysis |  |  | X | X
Identify and Document Assumptions | X | X | X | X
Identify and Evaluate Architecture Risks | X | X | X | X
Business Architecture Work
Model High Level Processes | X | X | X | X
Model Mid Level Processes |  | X | X | X
Model Low level processes |  |  | X | X
Generate Process Hierarchy |  |  | X | X
Define the Business Services | X | X | X | X
Build Business Services Decomposition |  | X | X | X
Associate Business Services to automation |  | X | X | X
Information Architecture Work
Build Information Map | X | X | X | X
Build Logical Data Model |  | X | X | X
Build Logical Data Components |  | X | X | X
Build Physical Data Components |  |  | X | X
Support Data Security Classification |  | X | X | X
Support Data Governance Activity |  | X | X | X
Application Architecture Work
Define & Associate relevant Business Applications | X | X | X | X
Build System Architecture diagram | X | X | X | X
Define Interfaces |  | X | X | X
Generate Data Flow to Applications Matrix |  | X | X | X
Generate Data Flow to Data Components |  |  | X | X
Generate Application to Interface matrix |  |  | X | X
Technology Architecture Work
Model Network Topology | X | X | X | X
Define & Associate Technologies for deployment | X | X | X | X
Deployment diagram |  | X | X | X
Security Architecture |  | X | X | X
Deliverables
Create Architecture Definition Document |  |  | X | X
Review HLD | X | X | X
Review Decomposed HLD(s) |  |  |  | X
Review ICD(s) |  | X | X | X
ARB minutes | X | X | X | X
Present ARB | Architect Decides | X | X | X
Present Optional ARB |  | Optional | Recommended | Recommended

## Risk Assessment
Impact | Financial | Compliance | Operational |  | Reputational | Health , Safety and Environment
| Financial | Fraud and Regulatory Compliance | Operational | Process Breach | Media | Health & Safety | Environment
Notable (1) | • Financial losses of less than 0.01% of total assets value • Adverse impact on costs or revenues less than 0.05% | • No legal or regulatory compliance consequences • No fraud scenario identified • No internal or external investigation required • No civil liabilities | • Disruption of service capacity for 2 to less than 3 hours | • Results in reduced efficiency • No Financial loss • No Fraud scenario identified | • 1 day (or one time) negative media coverage on minor channels, with no impact on reputation Social Media Conversation that does not pick-up between customers | • Minor Injuries. which may require self-administered first aid to Customer/third party or personnel; • Injured personnel can continue to perform normal duties | • Temporary nuisance from noise, odour, dust and other air emissions, greenhouse gases, vibration, visual impact, minor uses of water, fuels, energy and other natural resources
Minor (2) | • Financial Losses of 0.01-0.04 % of total assets value • Adverse impact on revenues or costs of 0.05-0.2 % | •Minor non-compliance not likely to result in any regulatory action against the company • Financial loss resulting from negligence or fraud (less than USD 50,000) • Internal investigation • No civil liabilities • Minor enhancement of internal processes required • No notification required | • Disruption of service capacity for 3 to 9 hours | • Results in reduced efficiency • Fraud resulting in minor non-financial impact. | • 1-2 days of negative media coverage in media, but can be managed by effective communication Social Media Conversation may start to pick-up between customers who support each other | • Customer/third party or personnel Injuries requiring on-site treatment by medical practitioner • Personnel unable to continue to perform duties for a short period of time | • Contained release • Minor environmental impact due to contained release of pollutant, fire, or explosion with no lasting detrimental effects • No outside assistance required
Moderate (3) | • Financial Losses of 0.04-0.2 % of total assets value • Adverse impact on revenues or costs of 0.2-0.5% | • Penalties / fines as a result of regulatory violations of up to USD 100,000 • Moderate potential for some civil action against the company • Warning issued by regulator • Order to comply issued by regulator • May necessitate minor voluntary self-disclosure • Financial loss resulting from negligence or fraud (between USD 50,000 and 250,000) • Potential external investigation • Moderate enhancement of internal processes required. • Mandatory notification requirements apply | • Disruption of service capacity between 1 and less than 3 days | • Sequence of steps of established processes not followed, resulting in financial loss resulting from negligence or fraud. | • Short term regional negative media coverage (2 –3 days) concerning issues such as Guest service in local media with the potential to escalate • Brand reputation issues including: IP, copyright, defamation, and similar issues found anywhere on internet Social Media • Media pick-up on conversations or influencers with high reach | • Serious, but non-permanent injuries to Customer/third party or Personnel (i.e. loss time injury) requiring offsite treatment by medical practitioner or immediate evacuation to hospital • Potential long-term or moderate disabling effects | • Localized effect • Minor uncontained releases. • Creation of noise, odors, dust, other controlled / uncontrolled air emissions, greenhouse gases, vibration, and visual impact at moderate nuisance levels | Risk Score
Significant (4) | • Financial Losses of 0.2 – 0.5 % of total assets value • Adverse impact on revenues or costs of 0.5-1% • External audit management letter contains significant issues relating to P&L/financials | • Breach of Civil law of several countries • Serious regulatory violations resulting in fines amounting to USD 100,000 – 1,000,000 • Significant potential for civil action against the company (including class actions) • Necessitates voluntary self-disclosure of a serious breach • Financial loss resulting from negligence or fraud (between USD 250,000 and 1 MLN) •External investigation •Significant potential for bans to be imposed by regulators (denial of export privileges or ban on processing) • Significant enhancement of internal processes required | • Disruption of service capacity between 3 and 6 days | • Majority of steps of established process not followed • Complete breakdown of processes. | • Extensive global negative media coverage (3 – 5 days) relating to safety, security and / or financial matters • Brand reputation issues that attack the business or are highly explicit Social Media • High pick-up in conversations that continue to grow over 2+ hours over multiple customers (rough volume usually at 50+ interactions | • One fatality and / or permanent disability with serious illness or health impairment | • Significant environmental impact due to uncontained release, fire or explosion with detrimental effects • External assistance required • Results in the generation of significant quantities of hazardous wastes • Significant use of water, fuels and energy and natural resources
Major (5) | • Financial losses in excess of 0.5 % of total assets value • Adverse impact on revenues or costs of more than 1% • External audit qualification on the report and accounts • Major restatement of financials due to material errors/miscalculations | • Breach of criminal law as well as civil law in several countries • Operator license revoked / suspended • Serious regulatory violations resulting in fines in excess of USD 1,000,000 • Very high potential for large civil class actions against the company • Necessitates voluntary self-disclosure of a very major breach • Extensive regulatory investigations and possible criminal prosecution • Possibility that onerous supervisory orders might be imposed • Financial / non-financial loss resulting from negligence or fraud valued greater than USD 1 MN • Major enhancement of internal processes required | • Disruption of service capacity for more than 6 days | • Complete breakdown of processes resulting in financial / non-financial loss resulting from negligence or fraud. | • Widespread global negative media reports for > 5 days • Material change in public perception as a safe, high quality airline • Company is seen as unable to manage its operations Social Media • High pick-up in conversations that continue to grow over 2+ hours over multiple customers (rough volume usually at 50+ interactions | • Multiple fatalities and / or permanent disabilities with serious illness or health impairments | • Catastrophic environmental impact due to uncontained release, fire, or explosion with detrimental effects • Outside assistance required • Extensive chronic discharge of persistent hazardous pollutant • Results in generation of significant quantities of untraceable wastes
| Likelihood | Description |  |  |  |  | Probability of Occurrence
| Rare (1) | §Almost inconceivable to occur / very rare to occur in the Company |  |  |  |  | 0-5%
§Not yet occurred in the industry
§Occurs at a maximum once every 20 years in the Company
| Possible (2) | §Very unlikely to occur / not known to have occurred in the Company |  |  |  |  | 5-20%
|  | §Has occurred in the industry | [5 empty] | 10
|  | §Occurs at a maximum once every 5 years / at least once in 20 years in the Company | [5 empty] | 8
| Likely (3) | §Might occur in most circumstances in the Company |  |  |  |  | 20-50% | 3
|  | §Occurs at a maximum of once per year / at least once in 5 years in the Company | [5 empty] | 1
| Often (4) | §Likely to occur sometimes / has occurred infrequently in the Company |  |  |  |  | 50-80%
§Occurs at least once every 2 months / at least once per year in the Company
| Frequent (5) | §Likely to occur many times / has occurred frequently in the Company |  |  |  |  | 80-100%
§Occurs at least once per month in the Company

## Risk Heat Map
Risk | Score | Risk Description |  |  | INHERENT RISK HEATMAP
Extreme Risk | 10 | Immediate action required to mitigate the risk
High Risk | 7 | Action should be taken to compensate for the risk | LIKELIHOOD | Frequent (5) | Moderate Risk | High Risk | High Risk | Extreme Risk | Extreme Risk
Moderate Risk | 3 | Action should be taken to monitor the risk |  | Often (4) | Moderate Risk | Moderate Risk | High Risk | High Risk | Extreme Risk
Low Risk | 1 | Routine acceptance of the risk |  | Likely (3) | Moderate Risk | Moderate Risk | Moderate Risk | High Risk | High Risk
|  |  |  | Possible (2) | Low Risk | Moderate Risk | Moderate Risk | Moderate Risk | High Risk
|  |  |  | Rare (1) | Low Risk | Low Risk | Moderate Risk | Moderate Risk | Moderate Risk
[5 empty] | Notable (1) | Minor (2) | Moderate (3) | Significant (4) | Major (5)
IMPACT

## Values (hidden)
Profile Table |  |  | Simple | Medium | Medium | Complex | Very complex | For High Reusability | For Secret Data
Level | Rating |  | Assigned Architect | Assigned Architect +1 Lead | Assigned Architect +2 or +3 | Assigned Architect +4 Lead | Chief Architect | +Abdul | +Alan
Head of | 1 | Score Range | 0-40 | 41-50 | 51-60 | 61-80 | 81-100
VP | 4
SVP | 7 | Score | #REF! | Rounded Score |  | #REF!
Chief | 10
Cost/Investment Table |  | Score Range |  |  |  |  | Risk Likelihood |  |  | Risk Impact
Range | Rating | 0 | Simple | Assigned Architect |  |  | Rare (1) |  |  | Notable (1)
0-50k | 1 | 1 | Simple | Assigned Architect |  |  | Possible (2) |  |  | Minor (2)
50k-250k | 2 | 2 | Simple | Assigned Architect |  |  | Likely (3) |  |  | Moderate (3)
250k-500k | 4 | 3 | Simple | Assigned Architect |  |  | Often (4) |  |  | Significant (4)
500k-1M | 5 | 4 | Simple | Assigned Architect |  |  | Frequent (5) |  |  | Major (5)
1M-5M | 7 | 5 | Simple | Assigned Architect
5M+ | 9 | 6 | Simple | Assigned Architect
20M+ | 10 | 7 | Simple | Assigned Architect
|  | 8 | Simple | Assigned Architect
Data Classification Table | Rating | 9 | Simple | Assigned Architect
Public | 1 | 10 | Simple | Assigned Architect
Restricted | 5 | 11 | Simple | Assigned Architect
Confidential | 9 | 12 | Simple | Assigned Architect
Secret | 17 | 13 | Simple | Assigned Architect
|  | 14 | Simple | Assigned Architect
# of Impacted Interfaces Table | Rating | 15 | Simple | Assigned Architect
0-1 | 1 | 16 | Simple | Assigned Architect
2-4 | 5 | 17 | Simple | Assigned Architect
5-10 | 8 | 18 | Simple | Assigned Architect
11+ | 10 | 19 | Simple | Assigned Architect
|  | 20 | Simple | Assigned Architect
Reusability Table |  | 21 | Simple | Assigned Architect
High | 10 | 22 | Simple | Assigned Architect
Medium | 5 | 23 | Simple | Assigned Architect
Low | 1 | 24 | Simple | Assigned Architect
|  | 25 | Simple | Assigned Architect
|  | 26 | Simple | Assigned Architect
|  | 27 | Simple | Assigned Architect
Yes |  | 28 | Simple | Assigned Architect
No |  | 29 | Simple | Assigned Architect
|  | 30 | Simple | Assigned Architect
|  | 31 | Simple | Assigned Architect
|  | 32 | Simple | Assigned Architect
|  | 33 | Simple | Assigned Architect
|  | 34 | Simple | Assigned Architect
|  | 35 | Simple | Assigned Architect
|  | 36 | Simple | Assigned Architect
|  | 37 | Simple | Assigned Architect
|  | 38 | Simple | Assigned Architect
|  | 39 | Simple | Assigned Architect
|  | 40 | Simple | Assigned Architect
|  | 41 | Medium | Assigned Architect +1 Lead
|  | 42 | Medium | Assigned Architect +1 Lead
|  | 43 | Medium | Assigned Architect +1 Lead
|  | 44 | Medium | Assigned Architect +1 Lead
|  | 45 | Medium | Assigned Architect +1 Lead
|  | 46 | Medium | Assigned Architect +1 Lead
|  | 47 | Medium | Assigned Architect +1 Lead
|  | 48 | Medium | Assigned Architect +1 Lead
|  | 49 | Medium | Assigned Architect +1 Lead
|  | 50 | Medium | Assigned Architect +1 Lead
|  | 51 | Medium | Assigned Architect +2 or +3 Leads
|  | 52 | Medium | Assigned Architect +2 or +3 Leads
|  | 53 | Medium | Assigned Architect +2 or +3 Leads
|  | 54 | Medium | Assigned Architect +2 or +3 Leads
|  | 55 | Medium | Assigned Architect +2 or +3 Leads
|  | 56 | Medium | Assigned Architect +2 or +3 Leads
|  | 57 | Medium | Assigned Architect +2 or +3 Leads
|  | 58 | Medium | Assigned Architect +2 or +3 Leads
|  | 59 | Medium | Assigned Architect +2 or +3 Leads
|  | 60 | Medium | Assigned Architect +2 or +3 Leads
|  | 61 | Complex | Assigned Architect +2 or +3 Leads
|  | 62 | Complex | Assigned Architect +2 or +3 Leads
|  | 63 | Complex | Assigned Architect +2 or +3 Leads
|  | 64 | Complex | Assigned Architect +2 or +3 Leads
|  | 65 | Complex | Assigned Architect +4 Leads
|  | 66 | Complex | Assigned Architect +4 Leads
|  | 67 | Complex | Assigned Architect +4 Leads
|  | 68 | Complex | Assigned Architect +4 Leads
|  | 69 | Complex | Assigned Architect +4 Leads
|  | 70 | Complex | Assigned Architect +4 Leads
|  | 71 | Complex | Assigned Architect +4 Leads
|  | 72 | Complex | Assigned Architect +4 Leads
|  | 73 | Complex | Assigned Architect +4 Leads
|  | 74 | Complex | Assigned Architect +4 Leads
|  | 75 | Complex | Assigned Architect +4 Leads
|  | 76 | Complex | Assigned Architect +4 Leads
|  | 77 | Complex | Assigned Architect +4 Leads
|  | 78 | Complex | Assigned Architect +4 Leads
|  | 79 | Complex | Assigned Architect +4 Leads
|  | 80 | Complex | Assigned Architect +4 Leads
|  | 81 | Very Complex | Chief Architect
|  | 82 | Very Complex | Chief Architect
|  | 83 | Very Complex | Chief Architect
|  | 84 | Very Complex | Chief Architect
|  | 85 | Very Complex | Chief Architect
|  | 86 | Very Complex | Chief Architect
|  | 87 | Very Complex | Chief Architect
|  | 88 | Very Complex | Chief Architect
|  | 89 | Very Complex | Chief Architect
|  | 90 | Very Complex | Chief Architect
|  | 91 | Very Complex | Chief Architect
|  | 92 | Very Complex | Chief Architect
|  | 93 | Very Complex | Chief Architect
|  | 94 | Very Complex | Chief Architect
|  | 95 | Very Complex | Chief Architect
|  | 96 | Very Complex | Chief Architect
|  | 97 | Very Complex | Chief Architect
|  | 98 | Very Complex | Chief Architect
|  | 99 | Very Complex | Chief Architect
|  | 100 | Very Complex | Chief Architect
Note on B22: Naseemul Haq: Secret has a higher score to push sizing to Medium threshold with all other values at minimum